Pilot project - India
ACCESS TO EDUCATION AND HEALTHCARE FOR ETHNIC AND RELIGIOUS MINORITY YOUTH IN INDIA
Research Question and Design:
Exclusion of young people in relation to mental health and education.
Survey data already collected on  mental health of college students across India. Research plan:
  - analysis of survey data to identify subgroup inequities.
  - Further qualitative data from relevant stakeholders  and disadvantaged young people
  - Support for young people to engage with data analysis and development of possible solutions.
  - Workshop at the end of the study to bring stakeholders together and negotiate further action.

---
Study progress and political context
Ethical approval granted by University of Leeds to conduct study
  - Ethical approval in India refused – partners reported political and institutional context hostile to religious minorities
  - Partner a government funded body – own ethics panel would not approve the study
  - Switch to focus on tribal populations seen as more feasible – suggestion by Ethics Chair
  - Rewritten proposal submitted to ethics panel but no progress reported
  1. Survey analysis/context review did not require ethical approval
  - Gradual disengagement of partners and non-completion of the study
  - Continued engagement with a separate large mental health study suggests this was a more sensitive topic difficult to take forward in the current climate with government funded partner
  - Limited resources for the study a possible additional factor
  - NGOs reported as being prevented from research at same time, alternative partners difficult in project timescale
  1. Context of greatest need for intervention but most difficult to achieve – political rather than research action needed?